## Size Estimating Template (hidden)
Size Estimating Template
Student | Juan Camilo Mendieta Silva |  |  |  |  | Date |  | 2013-02-17
Program | Programa 4 – Calculo Rangos de Tamaño LOC usando Desviación Estándar |  |  |  |  | Program # |  | 4
Instructor | Luis Daniel Benavides |  |  |  |  | Language |  | JAVA
Estimated
Base Parts |  | Base |  | Deleted |  | Modified |  | Added
|  | 0 |  | 0 |  | 0 |  | 0
Total | B | 0 | D | 0 | M | 0 | BA | 0
Actual
Base Parts |  | Base |  | Deleted |  | Modified |  | Added
|  | 0 |  | 0 |  | 0 |  | 0
Total |  | 0 |  | 0 |  | 0 |  | 0
|  | Estimated | [6 empty] | Actual
Parts Additions |  | Type |  | Items |  | Rel. Size |  | Size* | Size* | Items
RangoTamanoRelativo |  | Data |  | 4 |  | S |  | 19.16 | 23 | 5
CalculoTamanoRelativo |  | Calc |  | 1 |  | M |  | 11.25 | 15 | 1
PanelCalculoTamanoRelativo |  | I/O |  | 2 |  | M |  | 32.3 | 51 | 2
InterfazCalculoRangoTamaoRelativoDE (Principal) |  | I/O |  | 3 |  | L |  | 64.86 | 63 | 2
CalculoTamanoRelativoTest |  | Set-Up |  | 1 |  | S |  | 5.04 | 24 | 1
Calculo (Se marca con *, para determinar que es reutilizable) |  | Calc |  | 2 |  | M |  | 11.25 | 13 | 2
Total | [6 empty] | PA | 143.86 | 189 | 13
|  | Estimated |  | Actual
Reused Parts |  | Size |  | Size
Calculo |  | 43 |  | 57
Lista |  | 51 |  | 51
Nodo |  | 25 |  | 25
PanelEncabezado |  | 21 |  | 21
Total | R | 140 |  | 154
PROBE Calculation Worksheet (Added and Modified) |  | Size |  | Time
Added size (A): A = BA+PA |  | 143.86
Estimated Proxy Size (E): E = BA+PA+M |  | 143.86
PROBE estimating basis used: (A, B, C, or D) |  | C |  | C
Correlation: (R2) |  | N/A |  | N/A
Regression Parameters: b0 Size and Time |  | 0 |  | 0
Regression Parameters: b1 Size and Time |  | 0.38385 |  | 0.82957
Projected Added and Modified Size (P): P = b0size + b1size*E |  | 55.2201
Estimated Total Size (T): T = P + B - D - M + R |  | 195.2201
Estimated Total New Reusable (NR): sum of * items |  | 11.25
Estimated Total Development Time: Time = b0time + b1time*E |  |  |  | 119.3414
Prediction Range: Range |  | - |  | 116.7242
Upper Prediction Interval: UPI = P + Range |  | - |  | 236.0656
Lower Prediction Interval: LPI = P - Range |  | - |  | 2.6173
Prediction Interval Percent: |  | - |  | 90
NOTA:
Se utiliza la siguiente tabla, propuesta en el libro de PSP
C++ Object Size in LOC per Method
Category | VS | S | M | L | VL
Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
Text | 3.75 | 8 | 17.07 | 36.41 | 77.66

## PSP Time Recording Log (hidden)
PSP Time Recording Log
Student | Juan Camilo Mendieta Silva |  |  |  | Date | 2013-02-15
Program | Programa 4 – Calculo Rangos de Tamaño LOC usando Desviación Estándar |  |  |  | Program # | 4
Instructor | Luis Daniel Benavides |  |  |  | Language | JAVA
Project | Phase | Start Date and Time | Int. Time | Stop Date and Time | Delta Time | Comments
Programa 4 | Planning - Requerimientos | 2013-02-16 21:00 | 0 h | 2013-02-16 21:30 | 0,5 h | Se realiza la especificación de requerimientos
Programa 4 | Planning - Diseño Conceptual | 2013-02-16 21:30 | 0h | 2013-02-16 22:30 | 1h | Se realiza el diseño conceptual para la estimaciòn de tamaños para cada una de las partes y items
Programa 4 | Planning - Plan Summary Form - Size Estimate | 2013-02-16 23:00 | 0h | 2013-02-17 01:00 | 2h | Se completa el Plan Summary y la plantilla de estimaciòn de tamaños de acuerdo al metodo PROB
Programa 4 | Desarrollo - Diseño | 2013-02-17 08:00 | 0h | 2013-02-17 10:30 | 2,5h | Elaboraciòn diseño de clases de las entidades establecidas.
Programa 4 | Desarrollo - Codificacion | 2013-02-17 20:13 | 0h | 2013-02-17 22:42 | 2,56h | Se realiza la codificaciòn del proyectos
Programa 4 | Desarrollo - Pruebas | 2013-02-17 20:13 | 0h | 2013-02-17 22:42 | 0,8h | Se realiza las pruebas de cada uno de los casos propuestos en el enunciado del requerimiento, completando el formato de pruebas de usuario.

## Probe - Size
Metodo C - Probe
|  | Programa 1 | Programa 2 | Programa 3 | Programa 4 | Programa 5 | Total
Size Estimating Procedure 4C
(a+m) | actual total added and modified size to date | 0 | 253 | 321 | 241 | 221 | 1036
| plan total added and modified size to date | 0 | 298 | 566 | 807 | 1028 | 2699
| B0 | 0
| B1 = (actual total added and modified size to date/plan total added and modified size to date) | 0.38385 | [5 empty] | 145.75 | 102.025 | 43.725 | 189.475

## Probe - Time
Metodo C - Probe
|  | Programa 1 | Programa 2 | Programa 3 | Programa 4 | Programa 5 | Total
Time Estimating Procedure 5C
| actual total development time to date | 0 | 384 | 509 | 598 | 748 | 2239
| estimated – total added and modified size to date | 0 | 298 | 566 | 807 | 1028 | 2699
| B0 | 0
| B1 = (actual total development time to date/estimated – total added and modified size to date) | 0.82957

## PROBE Calculation Worksheet
PROBE Calculation Worksheet (Added and Modified) | Size | Time
Added size (A): A = BA+PA | 125
Estimated Proxy Size (E): E = BA+PA+M | 165
PROBE estimating basis used: (A, B, C, or D) | C | C
Correlation: (R2) | NA | NA
Regression Parameters: b0 Size and Time | 0 | 0
Regression Parameters: b1 Size and Time | 0.38385 | 0.82957
Projected Added and Modified Size (P): P = b0size + b1size*E | 63.3346
Estimated Total Size (T): T = P + B - D - M + R | 162.3346
Estimated Total New Reusable (NR): sum of * items | 10
Estimated Total Development Time: Time = b0time + b1time*E |  | 136.8785
Prediction Range: Range | 113.6342 | 95.8149
Upper Prediction Interval: UPI = P + Range | 275.9688 | 232.6934
Lower Prediction Interval: LPI = P - Range | 48.7004 | 41.0635
Prediction Interval Percent: | 70% | 70%

## calculos %
7% | Planning | 70 | 8.14% | 860
5% | desing | 50 | 5.814% | 860
1% | desing | 14 | 1.628% | 860
57% | code | 459 | 53.37% | 860
2% | code review | 20 | 2.326% | 860
13% | test | 0 | 0% | 860
15% | pos | 107 | 12.44% | 860
|  | 140 | 16.28% | 860

## worksheet
Summary | Plan |  | Actual |  | To Date
Size/Hour | 1.8037 |  | 3.7714
Planned Time | 90
Actual Time |  |  | 70
CPI (Cost-Performance Index)
(Planned/Actual)
% Reuse | 0 |  | 0 |  | 12.03%
% New Reusable | 0% |  | 5.82% |  | 5.82%
Test Defects/KLOC or equivalent | 0 |  | 0 |  | 0
Total Defects/KLOC or equivalent | 0 |  | 0 |  | 0
Yield % | 0 |  | 0 |  | 0
Program Size | Plan |  | Actual |  | To Date
Base (B) | 0 |  | 0
| (Measured) |  | (Measured)
Deleted (D) | 0 |  | 0
| (Estimated) |  | (Counted)
Modified (M) | 0 |  | 0
| (Estimated) |  | (Counted)
Added (A) | 63.3346 | 119
| (A+M − M) | (T − B + D − R)
Reused (R) | 99 | 145 |  | 29
| (Estimated) | (Counted)
Added and Modified (A+M) | 63.3346 | 46 |  | 903
| (Projected) | (A + M)
Total Size (T) | 162.3346 | 264 |  | 1028
| (A+M + B − M − D + R) | (Measured)
Total New Reusable | 2 | 15 |  | 17

## process quality index
| Planeado | Actual | To date
PQI | 0.010202 | 0.62794 | 0.62794
Desgin quality | 0.076923 | 0.28571 | 0.28571
Desgin review | 0.5 | 2 | 2
code review quality | 0.076923 | 0.28571 | 0.28571
code quality | 2 | 2 | 2
program quality | 1.7241 | 1.9231 | 1.9231
design time | 4 | 10 | 10
design review time | 1 | 10 | 10
coding time | 52 | 35 | 35
code review time | 2 | 5 | 5
KLOC | 5 | 5 | 5
compile defects | 0 | 0 | 0
unit test defects | 4 | 1 | 1

## LOC_X_HORA - Rango (hidden)
Actual | Programa 2 | Programa 3 | Programa 4 | Total Ponderado
LOC Adicionadas y Modificadas | 339 | 391 | 190 | 730
Nhoras | 8 | 5 | 2.56 | 13
LOC x hora | 42.375 | 78.2 | 74.2188 | 56.1538
Rango | Tiempo (horas) | Tiempo Promedio
Mínimo | 3.3949 | 2.6173 |  | 2.6173
Maximo | 1.8396
Tamaño Estimado | 143.86